## Test Client
Client Name | Anurag Technologies | Ops Study Doc
Implementation Rep
No of users: | 800
Decision Maker | Anurag.Yaparla@testmail.com
POC contact number | PH No: 8861125145
Their Organization Workflow | Desk Management + VMS + Meeting Room
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | Reports Customization, Email Templates
Timelines to setup & Go-Live | (3/4 Weeks) | Pending
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | File-based Datasync | Completed
| SSO Integration | Integrations and validation | Pending
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Direct check-in | Pending
|  | Attendance Tracking | Pending
| VMS Integrations | Visitor Management | Not Received |  | Need to confirm
|  | Self Checkin+Walkin & Invite | Not Received
Pending
| Meeting Rooms Integrations | Outlook Addin for meeting rooms | Completed
|  | G-Suite | Completed
|  | Native | Completed
Amenities
| Desk Management | Floor Plan PDF | Not Received
|  | Nomenclature/Seat Numbering | Not required
|  | Office and Floor Name | Not required
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Not Received
|  | Geocode | Not Received
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Completed
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Not Received
|  | Schedule Edit Cutoff | Pending
|  | Schedule Cancel Cutoff | Pending
|  | Booking Logout Cutoff | Not Received
|  | Booking Edit Cutoff | Pending
|  | No Show Policy | Completed
|  | Desk Auto Release | Pending
|  | Auto Absent | Completed
|  | Auto Absent Timing | Pending
|  | Recurring Bookings in Days (30 or 90) | Pending
|  | Advance Booking Restriction (30 Days Advance) | Pending
Desk Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Pending
Other Features:
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Pending
|  | Bulk Uploads(Specify which ones) | Completed
| Booking Best Practices (User) | Search for Employee | Pending
|  | Wayfinding | Pending
Data Migration | Migration if any |  | Yes
| Migration Confirmation from Client |  | No
Email templates: |  |  | Completed
| Q&A 1 |  | Pending
| Q&A 2 |  | Pending
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Mindsprint
Client Name | Vontier-Invenco (GIlbarco Veeder) | Ops Study Doc
Implementation Rep | Anirban Bhowmik | https://docs.google.com/spreadsheets/d/1FvDprHlcKlnrHhmutYsvJ9_hzla7URILJFfYkxFdR-U/edit?gid=421597886#gid=421597886
No of users: | 637
Decision Maker (contact number) | Supriya.Agarwal@vontier.com (9008432720)
POC contact number | jareena.jacob@vontier.com (9663899008) sailas.nuleka@invenco.com (9740572049)
Their Organization Workflow | Desk Management + VMS + Meeting Room
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | None
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | File-based Datasync | Completed
| SSO Integration | Integrations and validation | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | ScanQR | Completed
|  | Attendance Tracking | Completed
| VMS Integrations | Visitor Management | Completed
|  | Self Checkin+Walkin & Invite | Completed
Completed
| Meeting Rooms Integrations | Outlook Addin for meeting rooms | Not required | initially taken but later stepped back due to access rights(internal to vontier)
|  | G-Suite | No
|  | Native | No
Amenities
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Completed
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed
|  | Schedule Cancel Cutoff | Completed
|  | Booking Logout Cutoff | Completed
|  | Booking Edit Cutoff | Completed
|  | No Show Policy | Not required
|  | Desk Auto Release | Completed | REMOVE_SEAT
|  | Auto Absent | Completed
|  | Auto Absent Timing | Completed | 1 hour
|  | Recurring Bookings in Days (30 or 90) | Completed | 1 week
|  | Advance Booking Restriction (30 Days Advance) | Completed | 1 week
Desk Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Not required
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Not required
| Booking Best Practices (User) | Search for Employee | Yes
|  | Wayfinding | No
Data Migration | Migration if any |  | Not required
| Migration Confirmation from Client |  | Not required
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team: |  |  | Meeting room is present in contract but later client did not want to go with neither native nor integrated setup
Issues provided by the client from the time of implementation to hand-over |  |  | Only common issue: employee unable to login due to no OTP received: Resolution-> They need to add the user to their azure directory's workinsync sso group, which will automatically create the profile in the next sync.
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Momentive
Client Name | Vontier-Invenco (GIlbarco Veeder) | Ops Study Doc
Implementation Rep | Anirban Bhowmik | https://docs.google.com/spreadsheets/d/1FvDprHlcKlnrHhmutYsvJ9_hzla7URILJFfYkxFdR-U/edit?gid=421597886#gid=421597886
No of users: | 637
Decision Maker (contact number) | Supriya.Agarwal@vontier.com (9008432720)
POC contact number | jareena.jacob@vontier.com (9663899008) sailas.nuleka@invenco.com (9740572049)
Their Organization Workflow | Desk Management + VMS + Meeting Room
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | None
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | File-based Datasync | Completed
| SSO Integration | Integrations and validation | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | ScanQR | Completed
|  | Attendance Tracking | Completed
| VMS Integrations | Visitor Management | Completed
|  | Self Checkin+Walkin & Invite | Completed
Completed
| Meeting Rooms Integrations | Outlook Addin for meeting rooms | Not required | initially taken but later stepped back due to access rights(internal to vontier)
|  | G-Suite | No
|  | Native | No
Amenities
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Completed
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed
|  | Schedule Cancel Cutoff | Completed
|  | Booking Logout Cutoff | Completed
|  | Booking Edit Cutoff | Completed
|  | No Show Policy | Not required
|  | Desk Auto Release | Completed | REMOVE_SEAT
|  | Auto Absent | Completed
|  | Auto Absent Timing | Completed | 1 hour
|  | Recurring Bookings in Days (30 or 90) | Completed | 1 week
|  | Advance Booking Restriction (30 Days Advance) | Completed | 1 week
Desk Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Not required
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Not required
| Booking Best Practices (User) | Search for Employee | Yes
|  | Wayfinding | No
Data Migration | Migration if any |  | Not required
| Migration Confirmation from Client |  | Not required
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team: |  |  | Meeting room is present in contract but later client did not want to go with neither native nor integrated setup
Issues provided by the client from the time of implementation to hand-over |  |  | Only common issue: employee unable to login due to no OTP received: Resolution-> They need to add the user to their azure directory's workinsync sso group, which will automatically create the profile in the next sync.
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## MongoDB
Client Name | MongoDB | Ops Study Doc
Implementation Rep | Anurag Yaparla
No of users: | 850
Decision Maker (contact number) | alok.sharma@mongodb.com(9871340358)
POC contact number | ishan.deopa@mongodb.com(9711474399)
Their Organization Workflow | Desk Management + VMS + Meeting Room
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | CAP-2222, CAP-2176,
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | File-based Datasync | Not required
| SSO Integration | OKTA | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Direct check-in | Completed
|  | Attendance Tracking | Completed
| VMS Integrations | Visitor Management | Completed
|  | Self Checkin+Walkin & Invite | Completed
Completed
| Meeting Rooms Integrations | Outlook Addin for meeting rooms | Not required | initially taken but later stepped back due to access rights(internal to vontier)
|  | G-Suite | No
|  | Native | No
Amenities
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Completed
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed
|  | Schedule Cancel Cutoff | Completed
|  | Booking Logout Cutoff | Completed
|  | Booking Edit Cutoff | Completed
|  | No Show Policy | Not required
|  | Desk Auto Release | Completed | REMOVE_SEAT
|  | Auto Absent | Completed
|  | Auto Absent Timing | Completed | 1 hour
|  | Recurring Bookings in Days (30 or 90) | Completed | 1 week
|  | Advance Booking Restriction (30 Days Advance) | Completed | 1 week
Desk Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Not required
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Not required
| Booking Best Practices (User) | Search for Employee | Yes
|  | Wayfinding | No
Data Migration | Migration if any |  | Not required
| Migration Confirmation from Client |  | Not required
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team: |  |  | Meeting room is present in contract but later client did not want to go with neither native nor integrated setup
Issues provided by the client from the time of implementation to hand-over |  |  | Only common issue: employee unable to login due to no OTP received: Resolution-> They need to add the user to their azure directory's workinsync sso group, which will automatically create the profile in the next sync.
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Thyssenkrupp
Client Name | Thyssenkrupp | Ops Study Doc
Implementation Rep | Anirban Bhowmik | https://docs.google.com/spreadsheets/d/1FvDprHlcKlnrHhmutYsvJ9_hzla7URILJFfYkxFdR-U/edit?gid=421597886#gid=421597886
No of users: | 1800
Decision Maker (contact number) | Supriya.Agarwal@vontier.com (9008432720)
POC contact number | jareena.jacob@vontier.com (9663899008) sailas.nuleka@invenco.com (9740572049)
Their Organization Workflow | Desk Management + VMS + Meeting Room
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | None
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | File-based Datasync | Completed
| SSO Integration | Integrations and validation | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | ScanQR | Completed
|  | Attendance Tracking | Completed
| VMS Integrations | Visitor Management | Completed
|  | Self Checkin+Walkin & Invite | Completed
Completed
| Meeting Rooms Integrations | Outlook Addin for meeting rooms | Not required | initially taken but later stepped back due to access rights(internal to vontier)
|  | G-Suite | No
|  | Native | No
Amenities
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Completed
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed
|  | Schedule Cancel Cutoff | Completed
|  | Booking Logout Cutoff | Completed
|  | Booking Edit Cutoff | Completed
|  | No Show Policy | Not required
|  | Desk Auto Release | Completed | REMOVE_SEAT
|  | Auto Absent | Completed
|  | Auto Absent Timing | Completed | 1 hour
|  | Recurring Bookings in Days (30 or 90) | Completed | 1 week
|  | Advance Booking Restriction (30 Days Advance) | Completed | 1 week
Desk Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Not required
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Not required
| Booking Best Practices (User) | Search for Employee | Yes
|  | Wayfinding | No
Data Migration | Migration if any |  | Not required
| Migration Confirmation from Client |  | Not required
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team: |  |  | Meeting room is present in contract but later client did not want to go with neither native nor integrated setup
Issues provided by the client from the time of implementation to hand-over |  |  | Only common issue: employee unable to login due to no OTP received: Resolution-> They need to add the user to their azure directory's workinsync sso group, which will automatically create the profile in the next sync.
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## WiproCollab
Client Name | WiproCollab | Ops Study Doc
Implementation Rep
No of users: | 800
Decision Maker | Anurag.Yaparla@testmail.com
POC contact number | PH No: 8861125145
Their Organization Workflow | Parking + VMS + ANPR
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | Reports Customization, Email Templates
Timelines to setup & Go-Live | (3/4 Weeks) | Pending
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | Manual Bulk Upload | Pending
| SSO Integration | Integrations and validation | Not required
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Direct check-in | Pending
|  | Attendance Tracking | Pending
| VMS Integrations | Visitor Management | Not Received |  | Need to confirm
|  | Walkin & Invite | Not Received
Pending
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Not Received
|  | Schedule Edit Cutoff | Pending
|  | Schedule Cancel Cutoff | Pending
|  | Booking Logout Cutoff | Not Received
|  | Booking Edit Cutoff | Pending
|  | No Show Policy | Completed
|  | Desk Auto Release | Pending
|  | Auto Absent | Completed
|  | Auto Absent Timing | Pending
|  | Recurring Bookings in Days (30 or 90) | Pending
|  | Advance Booking Restriction (30 Days Advance) | Pending
Desk Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Pending
Other Features:
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Pending
|  | Bulk Uploads(Specify which ones) | Completed
| Booking Best Practices (User) | Search for Employee | Pending
|  | Wayfinding | Pending
Data Migration | Migration if any |  | Yes
| Migration Confirmation from Client |  | No
Email templates: |  |  | Completed
| Q&A 1 |  | Pending
| Q&A 2 |  | Pending
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Vontier
Client Name | Vontier-Invenco (GIlbarco Veeder) | Ops Study Doc
Implementation Rep | Anirban Bhowmik | https://docs.google.com/spreadsheets/d/1FvDprHlcKlnrHhmutYsvJ9_hzla7URILJFfYkxFdR-U/edit?gid=421597886#gid=421597886
No of users: | 637
Decision Maker (contact number) | Supriya.Agarwal@vontier.com (9008432720)
POC contact number | jareena.jacob@vontier.com (9663899008) sailas.nuleka@invenco.com (9740572049)
Their Organization Workflow | Desk Management + VMS + Meeting Room
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | None
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | File-based Datasync | Completed
| SSO Integration | Integrations and validation | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | ScanQR | Completed
|  | Attendance Tracking | Completed
| VMS Integrations | Visitor Management | Completed
|  | Self Checkin+Walkin & Invite | Completed
Completed
| Meeting Rooms Integrations | Outlook Addin for meeting rooms | Not required | initially taken but later stepped back due to access rights(internal to vontier)
|  | G-Suite | No
|  | Native | No
Amenities
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Completed
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed
|  | Schedule Cancel Cutoff | Completed
|  | Booking Logout Cutoff | Completed
|  | Booking Edit Cutoff | Completed
|  | No Show Policy | Not required
|  | Desk Auto Release | Completed | REMOVE_SEAT
|  | Auto Absent | Completed
|  | Auto Absent Timing | Completed | 1 hour
|  | Recurring Bookings in Days (30 or 90) | Completed | 1 week
|  | Advance Booking Restriction (30 Days Advance) | Completed | 1 week
Desk Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Not required
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Not required
| Booking Best Practices (User) | Search for Employee | Yes
|  | Wayfinding | No
Data Migration | Migration if any |  | Not required
| Migration Confirmation from Client |  | Not required
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team: |  |  | Meeting room is present in contract but later client did not want to go with neither native nor integrated setup
Issues provided by the client from the time of implementation to hand-over |  |  | Only common issue: employee unable to login due to no OTP received: Resolution-> They need to add the user to their azure directory's workinsync sso group, which will automatically create the profile in the next sync.
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## PwC AC
Client Name | PwC AC | Configurations Document
Implementation Rep | Anurag Yaparla | Configurations Document
No of users: | 42000 | Handover Ops Doc
Decision Maker (contact number) | srinath.imarati@pwc.com (9880028659)
POC contact number | bhairavee.desai@pwc.com (9987774883) lipsa.mishra@pwc.com (9620900812)
Their Organization Workflow | Desk Management + Meeting Room
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | None
Timelines to setup & Go-Live | 10 Months(Office wise launch)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | SCIM | Completed
| SSO Integration | Integrations and validation | Completed
| Access card integration | Kantech | Pending
| Sign-In preference | ScanQR | Completed
|  | Attendance Tracking | Completed
| Meeting Rooms Integrations | Outlook Addin for meeting rooms | Not required
|  | G-Suite | Not required
|  | Native | Completed
|  | Amenities | Completed
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Not required
|  | Geo Restrictions | Completed
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed
|  | Schedule Cancel Cutoff | Completed
|  | Booking Logout Cutoff | Completed
|  | Booking Edit Cutoff | Completed
|  | No Show Policy | Completed
|  | Desk Auto Release | Completed | REMOVE_SEAT
|  | Auto Absent | Completed
|  | Auto Absent Timing | Completed | 1 hour
|  | Recurring Bookings in Days (30 or 90) | Completed
|  | Advance Booking Restriction (30 Days Advance) | Completed | 15 Days
Desk Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Not required
Trainings: |  |  | Completed
| Desk Management Best Practices (Admin) | Muli-Allocation | Completed
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Completed
|  | Desk Tags | Completed
|  | Bulk Uploads(Specify which ones) | Completed | Allocation & Tags
| Booking Best Practices (User) | Search for Employee | Completed
|  | Wayfinding | Not required
Data Migration | Migration if any |  | Completed | Migrated numerous Meeting & Cabin bookings
| Migration Confirmation from Client |  | Completed
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team: |  |  | Meeting room is present in contract but later client did not want to go with neither native nor integrated setup
Issues provided by the client from the time of implementation to hand-over |  |  | Only common issue: employee unable to login due to no OTP received: Resolution-> They need to add the user to their azure directory's workinsync sso group, which will automatically create the profile in the next sync.
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Indegene
Client Name | Indegene Global | Ops Study Doc
Implementation Rep | Anurag Yaparla
No of users: | 6000
Decision Maker (contact number) | jaisriram.krishnan@indegene.com (9449695616)
POC contact number | adoni.mohan@indegene.com (8884100415)
Their Organization Workflow | Desk Management + VMS + Meeting Room + Parking
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | CAP-1902 - "Active Bookings" – Weekly Limit Configuration
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | SCIM | Completed
| SSO Integration | Azure | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Direct check-in | Completed
|  | Attendance Tracking | Completed
| VMS Integrations | Visitor Management | Completed | Awaiting Feedback
|  | Self Checkin & Invite | Completed
Completed
| Meeting Rooms Integrations | Outlook Addin for meeting rooms | Completed | Outlook integrated setup - Mail ID: anurag.yaparla@indegene.com Password : P@An-Rga2ind
|  | G-Suite | No
|  | Native | No
Amenities
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Completed
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Not required
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed
|  | Schedule Cancel Cutoff | Completed
|  | Booking Logout Cutoff | Completed
|  | Booking Edit Cutoff | Completed
|  | No Show Policy | Not required
|  | Desk Auto Release | Completed | REMOVE_SEAT
|  | Auto Absent | Completed
|  | Auto Absent Timing | Completed | 2 hours
|  | Recurring Bookings in Days (30 or 90) | Completed | 30
|  | Advance Booking Restriction (30 Days Advance) | Completed | 30
|  | Active booking limit | Completed | Seto to 10 Active bookings
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Not required | Might request metabase dashboard at a later stage
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Completed | Desk Bookings & allocation
| Parking Management Best Practices (Admin) | Allocation | Completed
|  | Audit History | Completed
Booking Best Practices (User)
|  | Search for Employee | Yes
|  | Wayfinding | Not required
Data Migration |  |  | Not required
| Migration Confirmation from Client |  | Not required
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team: |  |  | Meeting room is present in contract but later client did not want to go with neither native nor integrated setup
Issues provided by the client from the time of implementation to hand-over |  |  | Only common issue: employee unable to login due to no OTP received: Resolution-> They need to add the user to their azure directory's workinsync sso group, which will automatically create the profile in the next sync.
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Coforge VMS
Client Name | Indegene Global | Ops Study Doc
Implementation Rep | Anurag Yaparla
No of users: | 6000
Decision Maker (contact number) | jaisriram.krishnan@indegene.com (9449695616)
POC contact number | adoni.mohan@indegene.com (8884100415)
Their Organization Workflow | Desk Management + VMS + Meeting Room + Parking
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | CAP-1902 - "Active Bookings" – Weekly Limit Configuration
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | SCIM | Completed
| SSO Integration | Integrations and validation | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Direct check-in | Completed
|  | Attendance Tracking | Completed
| VMS Integrations | Visitor Management | Completed | Awaiting Feedback
|  | Self Checkin & Invite | Completed
Completed
| Meeting Rooms Integrations | Outlook Addin for meeting rooms | Completed | Outlook integrated setup
|  | G-Suite | No
|  | Native | No
Amenities
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Completed
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Not required
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed
|  | Schedule Cancel Cutoff | Completed
|  | Booking Logout Cutoff | Completed
|  | Booking Edit Cutoff | Completed
|  | No Show Policy | Not required
|  | Desk Auto Release | Completed | REMOVE_SEAT
|  | Auto Absent | Completed
|  | Auto Absent Timing | Completed | 2 hours
|  | Recurring Bookings in Days (30 or 90) | Completed | 30
|  | Advance Booking Restriction (30 Days Advance) | Completed | 30
|  | Active booking limit | Completed | Seto to 10 Active bookings
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Not required | Might request metabase dashboard at a later stage
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Completed | Desk Bookings & allocation
| Parking Management Best Practices (Admin) | Allocation | Completed
|  | Audit History | Completed
Booking Best Practices (User)
|  | Search for Employee | Yes
|  | Wayfinding | Not required
Data Migration |  |  | Not required
| Migration Confirmation from Client |  | Not required
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team: |  |  | Meeting room is present in contract but later client did not want to go with neither native nor integrated setup
Issues provided by the client from the time of implementation to hand-over |  |  | Only common issue: employee unable to login due to no OTP received: Resolution-> They need to add the user to their azure directory's workinsync sso group, which will automatically create the profile in the next sync.
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Interglobe
Client Name | Interglobe | Ops Study Doc
Implementation Rep | Anurag Yaparla | Interglobe Ops Study Doc
No of users: | 600
Decision Maker (contact number) | parul.sirohi@interglobe.com ()
POC contact number | rakesh.rai@interglobe.com(8860111199)
Their Organization Workflow | VMS + Meeting Room
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | CAP-1902 - "Active Bookings" – Weekly Limit Configuration
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | SCIM | Completed
| SSO Integration | Integrations and validation | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Direct check-in | Completed
|  | Attendance Tracking | Completed
| VMS Integrations | Visitor Management | Completed | Awaiting Feedback
|  | Self Checkin & Invite | Completed
Completed
| Meeting Rooms Integrations | Outlook Addin for meeting rooms | Completed | Outlook integrated setup
|  | G-Suite | No
|  | Native | No
Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Not required | Might request metabase dashboard at a later stage
Trainings: |  |  | Completed
Booking Best Practices (User)
|  | Search for Employee | Yes
|  | Wayfinding | Not required
Data Migration |  |  | Not required
| Migration Confirmation from Client |  | Not required
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team: |  |  | Meeting room is present in contract but later client did not want to go with neither native nor integrated setup
Issues provided by the client from the time of implementation to hand-over |  |  | Only common issue: employee unable to login due to no OTP received: Resolution-> They need to add the user to their azure directory's workinsync sso group, which will automatically create the profile in the next sync.
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Aramex
Client Name | Aramex | Ops Study Doc
Implementation Rep | Anurag Yaparla
No of users: | 200
Decision Maker (contact number) | KrishnaK@aramex.com
POC contact number | TanishaV@aramex.com
Their Organization Workflow | Desk Management + MS Teams App
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | None
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | SCIM | Completed
| SSO Integration | Azure | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Direct check-in | Completed
|  | Attendance Tracking | Not required
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Completed
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed
|  | Schedule Cancel Cutoff | Completed
|  | Booking Logout Cutoff | Completed
|  | Booking Edit Cutoff | Completed
|  | No Show Policy | Not required
|  | Desk Auto Release | Completed | REMOVE_SEAT
|  | Auto Absent | Completed
|  | Auto Absent Timing | Completed | 1 hour
|  | Recurring Bookings in Days (30 or 90) | Completed | 1 week
|  | Advance Booking Restriction (30 Days Advance) | Completed | 1 week
Desk Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Not required
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Not required
| Booking Best Practices (User) | Search for Employee | Yes
|  | Wayfinding | No
Data Migration | Migration if any |  | Not required
| Migration Confirmation from Client |  | Not required
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team: |  |  | Meeting room is present in contract but later client did not want to go with neither native nor integrated setup
Issues provided by the client from the time of implementation to hand-over |  |  | Only common issue: employee unable to login due to no OTP received: Resolution-> They need to add the user to their azure directory's workinsync sso group, which will automatically create the profile in the next sync.
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Nielsen
Client Name | AnkoGCC | Ops Study Doc
Implementation Rep | Anurag Yaparla | Ops Configs
No of users: | 500
Decision Maker | Rajganesh & Sunil
POC contact number | Nageshraju: 9964056895 Facilities Manager
Their Organization Workflow | Desk Management + Meal Management
Key Pain Areas from previous system | Using Pro TMS for employee commute
Data migration | N/A
Promises/enhancements on features promised in demo | Reports Customization, Email Templates
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | SCIM | Completed
| SSO Integration | Azure AD | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Geofence check-in (+ mode) | Completed | Direct Checkin
|  | Attendance Tracking | Not required
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Not required
|  | Geo Restrictions | Not required
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed |  | 24
|  | Schedule Cancel Cutoff | Completed |  | 24
|  | Booking Logout Cutoff | Completed |  | 24
|  | Booking Edit Cutoff | Completed |  | 24
|  | No Show Policy | Not required
|  | Desk Auto Release | Not required
|  | Auto Absent | Not required
|  | Auto Absent Timing | Not required
|  | Advance Booking Restriction | Completed |  | 9 days
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Completed
Trainings:
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Completed
| Booking Best Practices (User) | Search for Employee | Completed
|  | Wayfinding | Not required | Not part of scope
Meal Management Best Practices (Admin)
|  | Meal configuration | Completed
Email templates:
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Innocean
Client Name | Innocean Worldwide | Ops Study Doc
Implementation Rep | Anurag Yaparla | Ops Study Doc
No of users: | 202
Decision Maker | Ugra Malik
POC contact number | Sudhakar 9990093663
Their Organization Workflow | Desk Management + VMS + Meeting Room
Key Pain Areas from previous system | Manual System
Data migration | No
Promises/enhancements on features promised in demo | Facial Recognition Access Control Integration
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | API | Not required | Manual Upload | Keka HR Integration may be requested without charges -To be discussed with Ashutosh Jakorta
| SSO Integration | Azure AD | Not required
| Access card integration | RSBarcodes | Completed | Facial Recognition Integration
| Sign-In preference | Direct check-in | Completed | 200 Mtr geofence
|  | Attendance Tracking | Not required
| Meeting Rooms Integrations | Native Setup for meeting rooms | Completed
|  | Meeting Room Addition | Completed
|  | Amenities | Completed
Restrictions/Parameters
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Not required | Not Part of scope
|  | Geo Restrictions | Completed
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Completed
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed |  | 4 hrs
|  | Schedule Cancel Cutoff | Completed |  | 4 hrs
|  | Booking Logout Cutoff | Completed |  | 0
|  | Booking Edit Cutoff | Completed |  | 0
|  | No Show Policy | Not required
|  | Desk Auto Release | Completed
|  | Auto Absent | Completed
|  | Auto Absent Timing | Completed |  | 2 hours
|  | Advance Booking Restriction | Completed |  | 30 days
|  | Desk Amenities | Completed
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Completed
Trainings:
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Completed
| Booking Best Practices (User) | Search for Employee | Completed
|  | Wayfinding | Not required | Not part of scope
Visitor Management Best Practices (Admin)
|  | Check In Method | Not required
Email templates:
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## AnkoGCC
Client Name | AnkoGCC | Ops Study Doc
Implementation Rep | Anurag Yaparla | Ops Configs
No of users: | 500
Decision Maker | Rajganesh & Sunil
POC contact number | Nageshraju: 9964056895 Facilities Manager
Their Organization Workflow | Desk Management + Meal Management
Key Pain Areas from previous system | Using Pro TMS for employee commute
Data migration | N/A
Promises/enhancements on features promised in demo | Reports Customization, Email Templates
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | SCIM | Completed
| SSO Integration | Azure AD | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Geofence check-in (+ mode) | Completed | Direct Checkin
|  | Attendance Tracking | Not required
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Not required
|  | Geo Restrictions | Not required
|  | Geocode | Completed
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed |  | 24
|  | Schedule Cancel Cutoff | Completed |  | 24
|  | Booking Logout Cutoff | Completed |  | 24
|  | Booking Edit Cutoff | Completed |  | 24
|  | No Show Policy | Not required
|  | Desk Auto Release | Not required
|  | Auto Absent | Not required
|  | Auto Absent Timing | Not required
|  | Advance Booking Restriction | Completed |  | 9 days
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Completed
Trainings:
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Completed
| Booking Best Practices (User) | Search for Employee | Completed
|  | Wayfinding | Not required | Not part of scope
Meal Management Best Practices (Admin)
|  | Meal configuration | Completed
Email templates:
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## EntainIVY
Client Name | Commvault | Ops Study Doc
Implementation Rep | Anurag Yaparla
No of users: | 3000
Decision Maker | Soumendra Dhar - Soumendra.Dhar@entainindia.com
POC contact number | PH No: Reach out to Anurag Chowdary Ravi/Vishwesh
Their Organization Workflow | Desk Management + VMS + Meal Management
Key Pain Areas from previous system | Manual System
Data migration | No
Promises/enhancements on features promised in demo | N/A
Timelines to setup & Go-Live | (3/4 Weeks) | Done
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | Manual Upload | Completed
| SSO Integration | Integrations and validation | Not required
| Access card integration | Lenel - SFTP | Pending
| Sign-In preference | Geofence check-in (+ mode) | Completed
|  | Attendance Tracking | Not required
| VMS Integrations | Visitor Management | Completed
|  | Self Checkin+Walkin & Invite | Completed
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Completed
|  | Geocode | Completed | 12.979594,77.663183
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
(Global and organizational settings)
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed
|  | Schedule Cancel Cutoff | Completed
|  | No Show Policy | Completed
|  | Desk Auto Release | Completed
|  | Auto Absent | Completed
|  | Recurring Bookings in Days (30 or 90) | Completed
|  | Desk Amenities | Completed
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
Other Features:
Trainings:
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed | Heirarchy based allocation
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Completed
|  | Bulk Uploads(Specify which ones) | Completed | Allocation, Desk booking
| Booking Best Practices (User) | Search for Employee | Completed
|  | Wayfinding | Completed
Data Migration | Migration if any |  | No
| Migration Confirmation from Client |  | No
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Commvault
Client Name | Commvault | Ops Study Doc
Implementation Rep | Anurag Yaparla
No of users: | 1400
Decision Maker | sushantrai@commvault.com
POC contact number | PH No: 9886122209
Their Organization Workflow | Desk Management + VMS + Meal Management
Key Pain Areas from previous system | Manual System
Data migration | No
Promises/enhancements on features promised in demo | N/A
Timelines to setup & Go-Live | (3/4 Weeks) | Done
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | Manual Upload | Completed
| SSO Integration | Integrations and validation | Not required
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Geofence check-in (+ mode) | Completed
|  | Attendance Tracking | Not required
| VMS Integrations | Visitor Management | Not required |  | Need to confirm
|  | Self Checkin+Walkin & Invite | Not required
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Completed
|  | Geocode | Completed | 12.979594,77.663183
|  | Shifts Creation | Completed
|  | Shift Categories | Completed
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
(Global and organizational settings)
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed | 12
|  | Schedule Cancel Cutoff | Completed | 4
|  | No Show Policy | Completed
|  | Desk Auto Release | Completed | 90 Minutes of no checkin
|  | Auto Absent | Completed | Marks Absent
|  | Recurring Bookings in Days (30 or 90) | Completed
|  | Desk Amenities | Completed | Dual Monitors & Height Adjustable
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
Other Features:
Trainings:
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed | Team Wise
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Completed | Allocation
| Booking Best Practices (User) | Search for Employee | Completed
|  | Wayfinding | Completed
Data Migration | Migration if any |  | No
| Migration Confirmation from Client |  | No
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Piraeus Bank
Client Name | Piraeus Bank | Ops Study Doc
Implementation Rep | Anurag Yaparla | SOW Doc
No of users: | 1400
Decision Maker | Makantassis Dimitris
POC contact number | NA
Their Organization Workflow | Desk Management + VMS + Meeting Room
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | Reports Customization, Email Templates
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | SCIM | Completed
| SSO Integration | Azure AD | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | No check-in | Not required
|  | Attendance Tracking | Not required
| Meeting Rooms Integrations | Native Setup for meeting rooms | Completed
|  | Meeting Room Addition | Completed
|  | Amenities | Completed
Restrictions/Parameters
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Not required
|  | Geo Restrictions | Not required
|  | Geocode | Not required
|  | Shifts Creation | Not required | 12 AM - 11:45 PM | Not visible to employees
|  | Shift Categories | Not required
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed |  | -24
|  | Schedule Cancel Cutoff | Completed |  | -24
|  | Booking Logout Cutoff | Completed |  | -24
|  | Booking Edit Cutoff | Completed |  | -24
|  | No Show Policy | Not required
|  | Desk Auto Release | Not required
|  | Auto Absent | Not required
|  | Auto Absent Timing | Not required
|  | Advance Booking Restriction | Completed |  | 15 days
|  | Desk Amenities | Completed
|  | Parking Tags | Completed
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Completed
Trainings:
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Completed
| Booking Best Practices (User) | Search for Employee | Completed
|  | Wayfinding | Not required | Not part of scope
Parking Management Best Practices (Admin)
|  | Check In Method | Not required
Email templates:
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## RMZ
Client Name | RMZ - Meeting Rooms | Ops Study Doc
Implementation Rep
No of users: | 800
Decision Maker | Anurag.Yaparla@testmail.com
POC contact number | PH No: 8861125145
Their Organization Workflow | Parking + VMS + ANPR
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | Reports Customization, Email Templates
Timelines to setup & Go-Live | (3/4 Weeks) | Pending
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | Manual Bulk Upload | Pending
| SSO Integration | Integrations and validation | Not required
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Direct check-in | Pending
|  | Attendance Tracking | Pending
| VMS Integrations | Visitor Management | Not Received |  | Need to confirm
|  | Walkin & Invite | Not Received
Pending
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Not Received
|  | Schedule Edit Cutoff | Pending
|  | Schedule Cancel Cutoff | Pending
|  | Booking Logout Cutoff | Not Received
|  | Booking Edit Cutoff | Pending
|  | No Show Policy | Completed
|  | Desk Auto Release | Pending
|  | Auto Absent | Completed
|  | Auto Absent Timing | Pending
|  | Recurring Bookings in Days (30 or 90) | Pending
|  | Advance Booking Restriction (30 Days Advance) | Pending
Desk Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Pending
Other Features:
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Pending
|  | Bulk Uploads(Specify which ones) | Completed
| Booking Best Practices (User) | Search for Employee | Pending
|  | Wayfinding | Pending
Data Migration | Migration if any |  | Yes
| Migration Confirmation from Client |  | No
Email templates: |  |  | Completed
| Q&A 1 |  | Pending
| Q&A 2 |  | Pending
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## Amazon SA
Client Name | Amazon SA | Ops Study Doc
Implementation Rep
No of users: | 800
Decision Maker | Anurag.Yaparla@testmail.com
POC contact number | PH No: 8861125145
Their Organization Workflow | Parking + VMS + ANPR
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | Reports Customization, Email Templates
Timelines to setup & Go-Live | (3/4 Weeks) | Pending
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | Manual Bulk Upload | Pending
| SSO Integration | Integrations and validation | Not required
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | Direct check-in | Pending
|  | Attendance Tracking | Pending
| VMS Integrations | Visitor Management | Not Received |  | Need to confirm
|  | Walkin & Invite | Not Received
Pending
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Not Received
|  | Schedule Edit Cutoff | Pending
|  | Schedule Cancel Cutoff | Pending
|  | Booking Logout Cutoff | Not Received
|  | Booking Edit Cutoff | Pending
|  | No Show Policy | Completed
|  | Desk Auto Release | Pending
|  | Auto Absent | Completed
|  | Auto Absent Timing | Pending
|  | Recurring Bookings in Days (30 or 90) | Pending
|  | Advance Booking Restriction (30 Days Advance) | Pending
Desk Amenities
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Pending
Other Features:
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Pending
|  | Bulk Uploads(Specify which ones) | Completed
| Booking Best Practices (User) | Search for Employee | Pending
|  | Wayfinding | Pending
Data Migration | Migration if any |  | Yes
| Migration Confirmation from Client |  | No
Email templates: |  |  | Completed
| Q&A 1 |  | Pending
| Q&A 2 |  | Pending
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## St Gobain
Client Name | Piraeus Bank | Ops Study Doc
Implementation Rep | Anurag Yaparla | SOW Doc
No of users: | 1400
Decision Maker | Makantassis Dimitris
POC contact number | NA
Their Organization Workflow | Desk Management + VMS + Meeting Room
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | Reports Customization, Email Templates
Timelines to setup & Go-Live | (3/4 Weeks)
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | SCIM | Completed
| SSO Integration | Azure AD | Completed
| Access card integration | Gallagher,Speedgates etc | Not required
| Sign-In preference | No check-in | Not required
|  | Attendance Tracking | Not required
| Meeting Rooms Integrations | Native Setup for meeting rooms | Completed
|  | Meeting Room Addition | Completed
|  | Amenities | Completed
Restrictions/Parameters
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed
|  | Office and Floor Name | Completed
|  | Wayfinding Deployment | Not required
|  | Geo Restrictions | Not required
|  | Geocode | Not required
|  | Shifts Creation | Not required | 12 AM - 11:45 PM | Not visible to employees
|  | Shift Categories | Not required
|  | Desk Allocation | Completed
|  | Remote Bookings | Not required
| (Global and organizational settings) |  | Completed
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed
|  | Hierarchy & Team Creation | Completed
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed |  | -24
|  | Schedule Cancel Cutoff | Completed |  | -24
|  | Booking Logout Cutoff | Completed |  | -24
|  | Booking Edit Cutoff | Completed |  | -24
|  | No Show Policy | Not required
|  | Desk Auto Release | Not required
|  | Auto Absent | Not required
|  | Auto Absent Timing | Not required
|  | Advance Booking Restriction | Completed |  | 15 days
|  | Desk Amenities | Completed
|  | Parking Tags | Completed
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
| Other Features: |  | Completed
Trainings:
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed
|  | Editing Allocation | Completed
|  | Time Based Allocation | Not required
|  | Desk Tags | Not required
|  | Bulk Uploads(Specify which ones) | Completed
| Booking Best Practices (User) | Search for Employee | Completed
|  | Wayfinding | Not required | Not part of scope
Parking Management Best Practices (Admin)
|  | Check In Method | Not required
Email templates:
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)

## RioTinto
Client Name | Anurag Technologies | Ops Study Doc
Implementation Rep
No of users: | 800
Decision Maker | Anurag.Yaparla@testmail.com
POC contact number | PH No: 8861125145
Their Organization Workflow | Desk Management
Key Pain Areas from previous system
Data migration | Yes
Promises/enhancements on features promised in demo | Reports Customization, Email Templates
Timelines to setup & Go-Live | (3/4 Weeks) | Pending
`
Level 1 | Level 2 | Level 3 | Status | Reason if not required | Comments if any | Path (JIRA Ticket, Config Value etc)
Integrations | Employee onboarding | File-based Datasync | Completed
| SSO Integration | Integrations and validation | Not required | Didn't initiate integration
| Access card integration | Gallagher,Speedgates etc | Not required | Didn't initiate integration
| Sign-In preference | Geofence check-in (+ mode) | Completed |  | Checkin Button
|  | Attendance Tracking | Not required
| Desk Management | Floor Plan PDF | Completed
|  | Nomenclature/Seat Numbering | Completed |  | Noted via manual efforts
|  | Office and Floor Name | Completed |  | RioTinto India 5A & RioTinto India 7B
|  | Wayfinding Deployment | Completed
|  | Geo Restrictions | Completed
|  | Geocode | Completed
|  | Shifts Creation | Completed |  | Shifts at Half hour intervals
|  | Shift Categories | Completed
|  | Shift Refreshment SE | Completed
|  | Desk Allocation | Completed |  | Team Wise allocation
|  | Remote Bookings | Completed |  | Enabled and customized
(Global and organizational settings)
General Setup |  | Company logo configuration | Completed
|  | Users & Roles Creation along with mobile access | Completed |  | Web & App
|  | Hierarchy & Team Creation | Completed |  | Teams created no heirarchy prsent at the moment
|  | Global Booking Policies | Completed
|  | Schedule Edit Cutoff | Completed |  | Can be edited up until the last minute of the planned booking time.
|  | Schedule Cancel Cutoff | Completed |  | Can be cancelled up until the last minute of the planned booking time.
|  | Booking Logout Cutoff | Completed
|  | Booking Edit Cutoff | Completed |  | Can be edited up until the last minute of the planned booking time.
|  | No Show Policy | Completed
|  | Desk Auto Release | Completed |  | 30 Mins of no checkin
|  | Auto Absent | Completed |  | 30 Mins of no checkin
|  | Recurring Bookings in Days (30 or 90) | Completed |  | 30
|  | Advance Booking Restriction (30 Days Advance) | Completed |  | 30
|  | Desk Amenities | Completed |  | Height Adjustable Desks
Template Customization
Please configure the below to drive usage of the account as per the flow of the account: | Reports |  | Completed
Other Features:
Trainings: |  |  | Completed
Desk Management Best Practices (Admin)
|  | Primary Method of Allocation | Completed |  | Team wise, few employee allocations
|  | Editing Allocation | Completed
|  | Time Based Allocation | Completed
|  | Desk Tags | Pending | Not received confirmation on the
|  | Bulk Uploads(Specify which ones) | Completed
| Booking Best Practices (User) | Search for Employee | Completed
|  | Wayfinding | Completed
Data Migration | Migration if any |  | Not required
| Migration Confirmation from Client |  | Not required
Email templates: |  |  | Completed
| Q&A 1 |  | Completed
| Q&A 2 |  | Completed
Important points to be noted while handing over the client to customer success team:
Issues provided by the client from the time of implementation to hand-over
Requirements provided while onboarding (mark in green if this requirement is completed. If not red if not completed/cannot implement it and yelllow if pending/taken as requirement)